## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W035-PEDCO-110-PI-DW-0001_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1618 |  |  | Transmital Date:11/27/2022
Document Title: Plot Plan Drawing - W035 |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PI-TR-1618 |  |  | Transmital Date: 11/27/2022
[5 empty] | CRS No: NISOC-CRS-BK-W035-PEDCO-110-PI-DW-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مختصات UTM مربوط به سلر چاه در نقشه اضافه شود. |  | 1401/988/382543 | 1401/10/10 | احتراما نقطه نظر اعمال گردید.
2 | اظهار نظر نهایی در خصوص محل گودال سوخت و هلی پد منوط به انجام بازدید میدانی(در صورت عدم انجام) با حضور ادارات ذیربط می باشد. |  | 1401/988/382543 | 1401/10/10 | احتراما این مورد مد نظر قرار می گیرد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: