## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W046S-PEDCO-110-PI-DW-0001_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1805 |  |  | Transmital Date:1/17/2023
Document Title: Plot Plan Drawing - W046S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-1805 |  |  | Transmital Date: 1/17/2023
[5 empty] | CRS No:NISOC-CRS-BK-W046S-PEDCO-110-PI-DW-0001_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مقرر گردید پایه روشنایی (تعداد و لوکیشن) آن ها در ویرایش بعد پس از اعمال نقطه نظرات کارفرما بروزرسانی و نهایی سازی به عمل آید |  | 1401/2294/472725 | 1401/12/09 | احتراما نقطه نظر اعمال گردید.
2 | مقرر گردید خط تولیدی PRODUCT LINE به سمت گودال های آب و گل منتقل گردد |  | 1401/2294/472725 | 1401/12/09 | احتراما نقطه نظر در مورد مدل سه بعدی می باشد که در مدل اعمال می گردید.
3 | مقرر گردید ساختمان برق به ضلع بالایی (دورترین فاصله از سر چاه) انتقال یابد. |  | 1401/2294/472725 | 1401/12/09 | احتراما نقطه نظر اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri G.Khisravizadegan | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 25-Jan-2023 |  |  |  |  | Date: 25-Jan-2023