## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-PI-PY-0002_D01 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-2059 |  |  | Transmital Date: 01-May-2023
Document Title: Plot Plan Drawing - W007S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-2059 |  |  | Transmital Date: 01-May-2023
[5 empty] | CRS No: PEDCO-CRS-BK-W007S-PEDCO-110-PI-PY-0002_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظرات بصورت مارك شده در مدرك به پيوست ارسال مي گردد. |  | BK-SUR-ENG-PIP-01-06909 | 2023-02-08 | احتراما پاسخ موارد به پیوست ارسال می گردد. |  |  | See Item 3
2 | با توجه به نامه شماره 19751 مورخ 22/01/1402 ذينفع اصلي كه ضميمه ايميل ميباشد، در مختصات IPهاي خط انتقال مربوط به چاه شماره 7 تغيير صورت پذيرفته است. لذا بررسي هاي لازم از سوي مشاور صورت پذيرد و در صورت نياز موقعيت خط انتقال و گنتري نشان داده شده در پلات پلن چاه شماه 7 اصلاح گردد |  | BK-SUR-ENG-PIP-02-07558 | 2023-05-06 | احتراما موارد به روز رسانی گردید.
3 | نظرات بصورت مارك شده در مدرك به پيوست ارسال مي گردد. |  | BK-SUR-ENG-PIP-02-07558 | 2023-05-06 | احتراما پاسخ موارد به پیوست ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri G.Khosravizadegan | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 6-May-2023 |  |  |  |  | Date: 6-May-2023