## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0001_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1384 |  |  | Transmital Date: 27/OCT/2022
Document Title: Mechanical Data Sheets For Inlet Gas K.O. Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-1384 |  |  | Transmital Date: 27/OCT/2022
[5 empty] | CRS No:NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0102_D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | اظهار نظر در خصوص داده برگ پس از نهایی شدن مدرک خوردگی و انتخاب مواد امکان پذیر می باشد. یادآور می شود موارد مربوطه پیشتر طی نامه شماره 01/2294/87483 اعلام شده است |  | 1401/2294/283322 | 1401/08/05 | مدرک مورد نظر (خوردگی و انتخاب مواد) در تاریخ 27/09/1401 با شماره ترانسمیتال T-1710 برای کارفرمای محترم ارسال شده است.
2 | نازل L5,6 مربوط به لول ترنسمیتر می باشد. |  | 1401/2294/283322 | 1401/08/05 | نظر کارفرمای محترم اعمال شد.
3 | با توجه به نوع سیال به نظر می رسد شرایط سرویس lethal نیز می بایست مد نظر قرار گیرند. |  | 1401/2294/283322 | 1401/08/05 | نظر کارفرمای محترم اعمال شد.
4 | نازل V2 و منهول می بایست در دو سوی مخالف یکدیگر نصب گردند. |  | 1401/2294/283322 | 1401/08/05 | نازل V2 و منهول در سوی مخالف یکدیگر قرار دارند. منهول به نازل V1 نزدیک تر است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: H.Adineh | Signature | M.Fakharian
| Date: |  |  |  |  | Date: 7/08/2023