## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0012-D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1396 |  |  | Transmital Date: 13/September/2022
Document Title: Mechanical Data Sheets For Flare K.O. Drum |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0109-ME-TR-1396 |  |  | Transmital Date: 13/September/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0012-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اینکه سیال داخل مخزن ترش می باشد لذا استاندارد NACE MR 0175 می بایست در نظر گرفته شود. |  | 01/2294/325846 | 1401/09/02 | در یادداشت 37 اشاره شده است.
2 | محل قرارگیری نازل ventilation و manhole باید در خلاف جهت یکدیگر باشد. |  | 01/2294/325846 | 1401/09/02 | نظر کارفر مای محترم اعمال شد.
3 | علت تغییر یادداشتهای 4 و 10 و 36 نسبت به ویرایش قبل می بایست با جزئیات کامل بیان گردد. |  | 01/2294/325846 | 1401/09/02 | نوت 4 به صورت کامل تر در نوت 14 اشاره شده است. و تغییرات یادداشت ها مطابق یادداشت های داده برگ های تایید شده می باشد.
نوت 10 بخاطر وجود نداشتن تجهیزات داخلی تغییر یافته است. و تغییرات یادداشت ها مطابق یادداشت های داده برگ های تایید شده می باشد.
نوت 36 در نوت 2 تکرار شده بود و و تغییرات یادداشت ها مطابق یادداشت های داده برگ های تایید شده می باشد.
4 | دلایل حذف یادداشت 13 و 28 با جزئیات کامل بیان گردد. |  | 01/2294/325846 | 1401/09/02 | نوت 28 مربوط به ابزار دقیق بوده است که در scope کاری وندور نیست و برای جلوگیری از سردرگمی سازنده تنها اشاره به spec شده است در مراجع و این نوت مطابق آنچه در مابقی دیتاشیت ها انجام شده بود حذف شده است.
نوت 13 تکراری می باشد و در نوت 1 گارانتی عملکرد بر عهده سازنده اشاره شده است. در ضمن این تغییرات در دیتاشبت های قبل نیز اعمال شده بود و کامنتی دریافت نشده بود.
5 | بند 43 به Spec مربوطه ارجاع گردد. |  | 01/2294/325846 | 1401/09/02 | در بند 29 به صورت جداگانه ارجاع شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.Naserizadeh |  |  | Clarified By: H.Adineh | Signature | M.Fakharian
| Date: 10/19/2022 |  |  |  |  | Date: 7/03/2023