## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0012-D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1396 |  |  | Transmital Date: 13/September/2022
Document Title: Mechanical Data Sheets For Flare K.O. Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0111-ME-TR-1396 |  |  | Transmital Date: 13/September/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-DT-0012-D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | F.V. / 7.5 |  | BK-SUR-ENG-MEC-01-05928 | 2022-10-18 | در ردیف 14 به صورت جداگانه مقدار internal vaccum مشخص شده است.
2 | برای نازل های بالای 2" می بایست reinforcement pad در نظر گرفته شود. |  | BK-SUR-ENG-MEC-01-05928 | 2022-10-19 | اعمال شد
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.Naserizadeh |  |  | Clarified By: H.Adineh | Signature | M.Fakharian
| Date: 10/19/2022 |  |  |  |  | Date: 7/03/2023