## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-LI-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1809 |  |  | Transmital Date: 1/21/2023
Document Title: Chemical Consumption List |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1809 |  |  | Transmital Date: 1/21/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-LI-0005_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق با پاسخ ارائه شده در CRS، ضروریست اصلاحات لازم در مدرک P&ID در خصوص نقاط تزریق متانول، اعمال گردد. |  | BK-SUR-ENG-PCS-01-06861 | 2023-02-01 | در مدرک اشاره شده اعمال گردید.
2 | نظری مطرح نمی باشد صرفا ضروریست نقطه نظرات ذینفع اصلی پروژه در مدرک اعمال گردد. |  | BK-SUR-ENG-PCS-01-06861 | 2023-02-01 | اعمال می‌گردد.
| نظری مطرح نمی باشد صرفا ضروریست نقطه نظرات ذینفع اصلی پروژه در مدرک اعمال گردد. |  | BK-SUR-ENG-PCS-02-08148 | 2023-07-24 | اعمال می‌گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021