## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-LI-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1809 |  |  | Transmital Date: 1/21/2023
Document Title: Chemical Consumption List |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1809 |  |  | Transmital Date: 1/21/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0005_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | اعداد محاسبه شده برای مواد ضد خوردگی با اعداد مندرج در جدول 1 گزارش ارسالی Chemical Consumption List-D02 مطابقت ندارد .ضروریست یکسان سازی گردد. |  | 1402/2294/86605 | 1402/03/07 | جدول 1 بر اساس اطلاعات شرکت ENERGY CHEMICAL CO Semnan اصلاح گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021