## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W028-PEDCO-110-GT-RT-0001 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-1572 |  |  | Transmital Date:11/5/2022
Document Title: Geotechnical Investigation Report - W028 |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-GT-T-1572 |  |  | Transmital Date:11/5/2022
[5 empty] | CRS No:NISOC-CRS-BK-W028-PEDCO-110-GT-RT-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1401-521-362164 | 1401/09/26 | لایه های مشاهده شده در محل سنگی بوده و امکان انجام آزمایشات آزمایشگاهی جهت تعیین نفوذپذیری وجود ندارد ، لذا با توجه به نفوذپذیری لایه های سنگی مقدار ارائه شده در گزارش کمتر از 7-^10 مطابق مراجع قابل پیشنهاد است
2 |  |  | 1401-521-362164 | 1401/09/26 | منابع قرضه و پارامترهای اساس و زیر اساس در پیوست ارائه می گردد
3 |  |  | 1401-521-362164 | 1401/09/26 | در محل گمانه های حفاری شده به پدیده کارست برخورد نشده است
4 |  |  | 1401-521-362164 | 1401/09/26 | در گزارش CBR برای اصلاح احتمالی جاده ارائه شده است
5 |  |  | 1401-521-362164 | 1401/09/26 | در بند 3-1 و 3-2 مشخصات گمانه ها و آزمایشات اشاره شده است
6 |  |  | 1401-521-362164 | 1401/09/26 | فصل مربوطه حذف گردید
Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Legend
| CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
Signature | Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: