## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W028-PEDCO-110-GT-RT-0001_D01 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-1572 |  |  | Transmital Date:11/5/2022
Document Title: Geotechnical Investigation Report - W028 |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-GT-T-1572 |  |  | Transmital Date:11/5/2022
[5 empty] | CRS No:NISOC-CRS-BK-W028-PEDCO-110-GT-RT-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | عليرغم آنكه درارتباط با كليه ترانسميتال هاي ارائه شده مشاور با موضوعيت گزارش هاي مكانيك خاك موقعيت هاي اجرايي ، نقطه نظرات بخش مهندسي پتروايران به تفصيل ارائه شده و در چندين مرحله نيز تاكيد گرديد تا كامنت ها اعمال و يا پاسخ داده شوند و گذشت بيش از يكسال از فعاليت هاي مهندسي و طراحي ، اقدام موثري در اين زمينه صورت نپذيرفته است. گزارش هاي مكانيك خاك ارائه شده پيوست ترانسميتال فوق نيز بدون اصلاح موارد (و يا پاسخ فني) ارائه گرديده اند و نقطه نظرات مطرح شده قبلي بر مدارك مشابه از جمله ترانسميتال 963 و 641 و 1018 به قوت خود باقي است. تنها موردي كه در فايل response sheet مشاور محترم به آن اشاره رفته آنست كه: "اطلاعات مربوط به لاگ های زمين شناسی و نتايج آزمايشات و پيوست و .... ارائه شد" ! |  | BK-SUR-ENG-CIV-01-06081 | 2022-11-05 | مدرک اصلاحی ارسال گردید
Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Legend
| CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
Signature | Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: