## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0005-D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1645 |  |  | Transmital Date: 29/Novr/2022
Document Title: PMR FOR STORAGE TANKS |  |  |  |  | PEDCO Tr. No. BK-PEDCO-NISOC-BK-ME-0005-T-01645 |  |  | Transmital Date: 29/Nov/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0005_D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
3 | ساختار کلی مدرک مورد تائید بوده و لیکن ارسال نسخه بعدی مدارک فوق منوط به نهایی سازی مدارک مرتبط مهندسی و درج نسخه تایید شده (AFC) است.معذالک جهت پرهیز از مکاتبات مضاعف و تسریع در تایید مدارک فوق،نهایی سازی مدارک پیش نیاز (که در پیوست 1 اشاره شده است) در دستور کار تیم مهندسی آن پیمانکار قرار گیرد.در ضمن MTO کالا نیز جزء مدارک خرید میبایست درج گردد. |  | 1401/2294/371137 | 1401/10/01 | باتوجه به تایید بیشتر مدارک پیوست 1 MR و همچنین عدم دریافت نقطه نظرات کلیدی، لذا از کارفرمای محترم خواهشمند است بررسی مدرک مذکور را در دستور کار قرار دهد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad | Signature | H.Naserizadeh |  |  | Clarified By: H.Ghadyani | Signature | M.Fakharian
| Date: 12/20/2022 |  |  |  |  | Date: