## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0010_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1385 |  |  | Transmital Date: 11/Sep/2022
Document Title: PMR For Centrifugal Pumps For General Services |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-1385 |  |  | Transmital Date: 11/Sep/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0010-D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در بند 5.1.2، عبارت "QA Organization" به "QA/QC Organization Chart" تغيير يابد. |  | BK-SUR-ENG-MEC-01-05836 | 2022-10-04 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته شده است
2 | در بند 6: -دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات به شماره مدرك ICE-EID-MI-SP02-REV-01 اضافه گردد. |  | BK-SUR-ENG-MEC-01-05836 | 2022-10-04 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته شده است
3 | در جدول Attachment 2: -در رديف 1، عبارت "See Attachment 2" حذف گردد. - عبارت "List of Documents will be Finalized in VPIS" در نوتها اضافه گردد. |  | BK-SUR-ENG-MEC-01-05836 | 2022-10-04 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته شده است
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Bavarsad M. Torkaman | Signature | H.Naserizadeh |  |  | Clarified By: S.Zafaresmaeili | Signature | M. Fakharian
| Date: 10/04/2022 |  |  |  |  | Date: 12/JUL/2023