## SHEET 1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0025_D05 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1978 |  |  | Transmital Date: 28/Mar/2023
Document Title: Mechanical Data Sheets For Potable Water Pump |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0201-ME-TR-1978 |  |  | Transmital Date: 28/Mar/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0025_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | صدور نسخه AFC پس از NO Comment شدن مدرک ارسال گردد. لذا با توجه به موارد مطروحه در نسخه پیشین مدرک صدور نسخه AFC پذیرفتنی نیست. |  | 1402-2294-30896 | 1402/01/30 | از آنجا که پیش تر مدارک با وضعیت AFC ارسال شده و امکان برگشت به وضعیت قبل وجود ندارد، لذا مدرک مجددا با وضعیت AFC ارائه می گردد
2 | توضیحات مندرج در بند 1، 2 و 3 برگ پاسخ (RS) مورد پذیرش نیست. این مدرک میبایست پس از نهایی سازی کلیه مدارک پیشنیاز ارائه و تایید گردد و مشروط کردن بخشهایی از مدرک پذیرفتنی نیست. |  | 1402-2294-30896 | 1402/01/30 | توضیحات بند 2,1 و 3 در برگ پاسخ (RS) ویرایش قبل مطابق با مدارک نهایی ارانه گردیده است.
3 | آخرین تغییرات اطلاعات فرآیندی در مدرک درج گردد. |  | 1402-2294-30896 | 1402/01/30 | اطلاعات فرآیندی مطابق با مدارک Process Data Sheets For Potable Water Pump و Calculation Note For Pumps میباشد همچنین لازم به ذکر است مدارک مذکور نهایی گردیده است .
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: S.Zafaresmaeili | Signature | M.Fakharian
| Date: |  |  |  |  | Date: 17/JUL/2023