## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-MR-0005_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2137 |  |  | Transmital Date: 23 May 2023
Document Title: PMR For Control Valves |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-2137 |  |  | Transmital Date: 23 May 2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-MR-0005_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | خدمات پس از فروش حداقل به مدت 10 سال در نظر گرفته شود. |  | 1402/2294/134366 | 1402/04/07 | مطابق نظر کارفرمای محترم اعمال گردید.
2 | در متن مدرک قبل از قسمت پیوست ها قید گردد ؛ آخرین نسخ مدارک پیوست (نسخه نهایی ) ملاک عمل می باشد. |  | 1402/2294/134366 | 1402/04/07 | مطابق نظر کارفرمای محترم اعمال گردید.
3 | جهت پرهیز از مکاتبات مضاعف و تسریع در تایید مدارک فوق ، نهایی سازی مدارک پیش نیاز ( که در پیوست 1 اشاره شده است ) در دستور کار تیم مهندسی آن پیمان کار قرار گیرد. |  | 1402/2294/134366 | 1402/04/07 | با توجه به نظر کارفرمای محترم و در جهت تسریع در انجام آتی ، مدرک مطابق آخرین نسخه از مدارک پیش نیاز نهیه گردید.
4 | تاکید میگردد از آنجا که مسئولیت طراحی تفضیلی پروژه جزو تعهدات پیمان کار پروژه بوده و هم چنین با استناد به وضعیت مدارک ارسالی(IFI) ، مسئولیت کامل عدم تطابق مندرج در این مدارک (مشخصات فنی و یا تعداد) در مرحله سفارش گذاری و خرید بر عهده آن پیمان کار می باشد . |  | 1402/2294/134366 | 1402/04/07 | نظر کارفرمای محترم ملاحظه گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: