## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-MR-0006_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1706 |  |  | Transmital Date: 17 Dec 2022
Document Title: PMR For Pressure Safety Valves (PSV) |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1706 |  |  | Transmital Date: 17 Dec 2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-MR-0006_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | جدول تجهیزات بدون جزئیات فنی ذکر گردد. برای جزئیات فنی به دیتاشیت و دیگر مدارک مهندسی پیوست ارجاع گردد. |  | 1401/2294/380503 | 1401/10/09 | مطابق نظر کارفرمای محترم اصلاح شد.
2 | جدول تجهیزات بجای قسمت جنرال مناسب است در قسمت SCOPE OF SUPPLY آورده شود. |  | 1401/2294/380503 | 1401/10/09 | مطابق نظر کارفرمای محترم اصلاح شد.
3 | خدمات پس از فروش حداقل 10 سال در نظر گرفته شود. |  | 1401/2294/380503 | 1401/10/09 | مطابق نظر کارفرمای محترم اصلاح شد.
4 | در متن مدرک قبل از قسمت پیوست ها قید گردد؛ آخرین نسخ مدارک پیوست (نسخه نهایی) ملاک عمل می باشد. |  | 1401/2294/380503 | 1401/10/09 | مطابق نظر کارفرمای محترم اصلاح شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: