## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-MT-0005_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1223 |  |  | Transmital Date: 31 Jul 2022
Document Title: MTO For Instrument Cable Tray/Ladder |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-1223 |  |  | Transmital Date: 31 Jul 2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-MT-0005_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | موارد 14 تا 19 قبل از عقد قرارداد مشخص گردد |  | 1401-2294-242351 | 1401/07/09 | ملاحظه گردید
2 | تسمه ( بست ) و متعلقات اتصال ارتینگ سینی های کابل در نظر گرفته شود |  | 1401-2294-242351 | 1401/07/09 | درخوست کارفرمای محترم در مدرک لحاظ گردید
3 | پیچ و مهره مناسب اتصال سینی کابل در نظر گرفته شود |  | 1401-2294-242351 | 1401/07/09 | در توضیحات مربوط به آیتم های 1 الی 4 ذکر شده است
4 | مدرک / مدارک مرتبط با این مدرک بعنوان مرجع ذکر گردد |  | 1401-2294-242351 | 1401/07/09 | درخوست کارفرمای محترم در مدرک لحاظ گردید
5 | مطابق آخرین ویرایش مدارک مرجع، مدرک بروز رسانی گردد |  | 1401-2294-242351 | 1401/07/09 | ملاحظه گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 16 Aug 2022 |  |  |  |  | Date: