## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-MR-0005_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2137 |  |  | Transmital Date: 23 May 2023
Document Title: PMR For Control Valves |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-IN-TR-2137 |  |  | Transmital Date: 23 May 2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-MR-0005_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي مي باشد. |  | BK-SUR-ENG-INS-02-07801 | 2023-06-03 | ملاحظه گردید.
2 | با توجه به اينكه مدارك پيش نياز اين مدرك نهايي نشده است، در صورت هر گونه تغيير در اين مدرك نيز بايد منعكس گردد. نهايي شدن شدن اين مدرك منوط به نهايي شدن مدارك پيش نياز مي باشد. |  | BK-SUR-ENG-INS-02-07801 | 2023-06-03 | ملاحظه گردید.
7 | لزوم ارائه مدارك ITP, QCP, MPS توسط سازنده قبل از برگزاري جلسه PIM در مدرك درج گردد. |  | BK-SUR-ENG-INS-02-07801 | 2023-06-03 | اعمال گردید.
8 | جهت يكسان سازي در كليه متون، كلمهVendor جايگزين Supplier گردد. |  | BK-SUR-ENG-INS-02-07801 | 2023-06-03 | اعمال گردید.
10 | در بند 5.1.1 عبارت QA organization به QA/QC organization تغيير يابد. |  | BK-SUR-ENG-INS-02-07801 | 2023-06-03 | اعمال گردید.
11 | در بند 5.1.2 شماره مدرك بصورت صحيح E&C-QC-SP-1 ذكر گردد. |  | BK-SUR-ENG-INS-02-07801 | 2023-06-03 | اعمال گردید.
12 | جهت يكسان سازي در كليه مدارك MR پروژه، نگارش توضيحات بند6 مطابق ذيل انجام گردد. |  | BK-SUR-ENG-INS-02-07801 | 2023-06-03 | اعمال گردید.
| The equipment shall be inspected and tested in accordance with the Inspection &Test plan (ITP) issued by the vendor and approved by the CLIENT/EPC CONTRACTOR before the award of the order . The Inspection & Test plan (ITP ) shall be at least according to the Commodity Procurement and Manufacturing Inspection Instruction ( Docs .Nos. ICE-EID-MI-SP01-Rev01) , Inspection Level of Commodity and Equipment ( Docs .Nos. ICE-EID-MI-SP02-Rev01) and Data Sheets. The vendor shall in any case conduct all the tests required by contractual documents, specifications, codes and standards, manufacturer standard quality system and keep the relevant documentation. All required manufacturing and function test/inspection also Factory Acceptance Test /Site Acceptance Test and Quality Assurance requirements shall be considered in vendor responsibility as per project specification. |  |  | 2023-06-03
13 | در بند (PRICE BREAKDOWN) ، در آيتم هاي شماره 3و2، شماره مدرك بصورت صحيح E&C-QC-SP-1 وارد گردد. |  | BK-SUR-ENG-INS-02-07801 | 2023-06-03 | اعمال گردید.
14 | در جدول Attachment 1 شماره مدرك مربوط به "دستورالعمل تامين قطعات يدكي" به صورت صحيح E&C-QC-SP-1 وارد گردد. |  | BK-SUR-ENG-INS-02-07801 | 2023-06-03 | اعمال گردید.
15 | در جدول Attachment 2 عبارت See attachment 2 حذف گردد. |  | BK-SUR-ENG-INS-02-07801 | 2023-06-03 | اعمال گردید.
16 | "List of Documents Will be Finalized in Vendor Document index and Schedule" به انتهاي جدول Attachment 2 اضافه گردد. |  | BK-SUR-ENG-INS-02-07801 | 2023-06-03 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 3 Jun 2023 |  |  |  |  | Date: