## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-MR-0006_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1706 |  |  | Transmital Date: 17 Dec 2022
Document Title: PMR For Pressure Safety Valves (PSV) |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1706 |  |  | Transmital Date: 17 Dec 2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-MR-0006_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-06562 | 2022-12-31 | ملاحظه گردید.
2 | جمله زير در انتهاي پيوست 2 درج شود: NOTE: List of Documents will be Finalized in VPIS |  | BK-SUR-ENG-INS-01-06562 | 2022-12-31 | اضافه گردید.
3 | جدول بخش 2 با مدرك Index تطابق ندارد، مدارك به روز رساني و همسان سازي گردد. |  | BK-SUR-ENG-INS-01-06562 | 2022-12-31 | تصحیح گردید.
4 | آيتم هاي ذكر شده در جدول بخش 2 با آخرين مدرك ديتاشيت نسخه D01 تناقض دارد. موارد مجددا بررسي و مدرك ارسال گردد. |  | BK-SUR-ENG-INS-01-06562 | 2022-12-31 | با توجه به نقطه نظر ذی نفع اصلی ، اطلاعات کاهش یافت و برای دسترسی به اطلاعات فنی ، به داده برگ رجوع گردد.
5 | نقطه نظرات ذي نفع اصلي در اين مدرك در نظر گرفته شود. |  | BK-SUR-ENG-INS-01-06562 | 2022-12-31 | ملاحظه گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 31 Dec 2022 |  |  |  |  | Date: