## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-GCS-PEDCO-120-AR-DW-0003_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1608 |  |  | Transmital Date:11/27/2022
Document Title:Architectural Drawing For Gas Compressors Shelter |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-AR-T-1608 |  |  | Transmital Date: 11/27/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-AR-DW-0003_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | بند 1 |  | 1401-2294-362801 | 1401/09/26 | تراز روی پیوینگ با هماهنگی بخش سیویل به +0.20 تغییر یافت و کلیه کدهای ارتفاعی اصلاح گردید.
2 | بند2 |  | 1401-2294-362801 | 1401/09/26 | در سرتاسر دهانه ها پوشش louver در نظر گرفته شد. باتوجه به قرارگیری louver وتامین نیاز و همچنین نظر بخش hvac, استفاده از فن ضرورت ندارد.
3 | بند3 |  | 1401-2294-362801 | 1401/09/26 | با هماهنگی بخش سیویل کانالهایی برای دفع آب های آلوده در نظر گرفته شد.
4 | بند4 |  | 1401-2294-362801 | 1401/09/26 | درز انبساطی توسط بخش سازه بررسی و در دهانه وسط سوله اعمال گردید.
5 | بند5 |  | 1401-2294-362801 | 1401/09/26 | ضخامت ورق پوششی در شیت ها اشاره گردید
7 | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
8
9 | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
10 | Commented By: | Signature |  |  |  | Clarified By: | Signature
11
12 | Date: |  |  |  |  | Date:
13
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
Legend
Signature