## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0011_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1536 |  |  | Transmital Date: 23/Oct/2022
Document Title: PMR For Fire Water Pump |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0108-ME-TR-1536 |  |  | Transmital Date: 23/Oct/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0011_D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به ضرورت تامين Mating flange توسط وندور پمپ ها ، اين موضوع در مدرك قيد گردد. |  | BK-SUR-ENG-MEC-01-06044 | 2022-10-31 | Already had been mentioned in scope of supply section
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.Naserizadeh |  |  | Clarified By: S.Zafaresmaeili | Signature | M. Fakharian
| Date: |  |  |  |  | Date: 17/Jul/2023