## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0008_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1575 |  |  | Transmital Date:5/NOV/2022
Document Title: PMR For Chemical Injection Packages |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0109-ME-TR-1575 |  |  | Transmital Date:5/NOV/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0008-D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ساختار کلی مدرک مورد تایید بوده لیکن ارسال نسخه بعدی این مدرک منوط به نهایی سازی مدارک مرتبطه مهندسی و درح نسخ تایید شده (AFC) در مدارک فوق الذکر میباشدو معذالک حهت پرهیز از مکاتبات مطاعف و تسریع در تایید مدارک فوق، نهایی سازی مدارک پیش نیاز(مندرج پیوست 1) در دستور کار تیم مهندسی آن پیمانکار قرار گیرد |  | 1401-2294-327165 | 1401/09/03 | مدرک MR پکیج خوردگی به همراه آخرین ویرایش مدارک مرجع (ATTACHMENT#1) خدمت کارفرمای محترم ارسال می گردد.با توجه به اینکه مدارک پیوست تقریباً نهایی شده است لذا خواهشمند است جهت تسریع در امور خرید بررسی مدرک مذکور در دستور کار آن کارفرمای محترم قرار گیرد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature | H.Naserizadeh |  |  | Clarified By: S.Zafaresmaeili | Signature | M. Fakharian
| Date: |  |  |  |  | Date: 22/Jul/2023