## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-PY-0003_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1304 |  |  | Transmital Date: 23 Aug 2022
Document Title: Instrument Location Layout |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1304 |  |  | Transmital Date: 23 Aug 2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-PY-0003_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-05616 | 2022-09-06 | ملاحظه گردید
2 | مدرك با PID مغايرت دارد براي مثال TIT-2104 و … در مدرك ديده نشده است. موارد مجددا بررسي و ارسال گردد. |  | BK-SUR-ENG-INS-01-05616 | 2022-09-06 | اعمال گردید
3 | تمامي ادوات در ا ين مدرك ديده شود مانند CC و CP. |  | BK-SUR-ENG-INS-01-05616 | 2022-09-06 | اعمال گردید
4 | فرمت ارائه مدرك اصلاح شود و موارد زير براي خوانايي در اين مدرك اعمال گردد. |  | BK-SUR-ENG-INS-01-05616 | 2022-09-06
5 | ليست equipment ها اضافه گردد. |  | BK-SUR-ENG-INS-01-05616 | 2022-09-06 | برای لیست تجهیزات به مدرکOveral Plot Plan مراجعه شود.
6 | صفحه انتقال به شيت ها مشخص شود كه دنباله هر صفحه در كدام شيت پيگيري شود. |  | BK-SUR-ENG-INS-01-05616 | 2022-09-06 | اعمال گردید
7 | Key Plan و نواحي آن تحت Legend در يك صفحه مجزا ذكر گردد. |  | BK-SUR-ENG-INS-01-05616 | 2022-09-06 | اعمال گردید
8 | equipment ها و ليست ابزار دقيق به كار رفته بر روي آنها در يك جدول ارائه گردد. |  | BK-SUR-ENG-INS-01-05616 | 2022-09-06 | مدرک INSTRUMENT INDEX و MODEL REVIEW 60% بعنوان مدرک REFRENCE اضافه گردید
9 | مشخص شود كه هر صفحه شامل چه Eqipment هايي هست. |  | BK-SUR-ENG-INS-01-05616 | 2022-09-06 | برای رفع ابهام مدرک INSTRUMENT INDEX و MODEL REVIEW 60% بعنوان مدرک REFRENCE اضافه گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 6 Sep 2022 |  |  |  |  | Date: