## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK14-PEDCO-110-CV-DW-0001 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2241 |  |  | Transmital Date: 06/22/2023
Document Title: Civil and Structural drawings - BK14 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-T-2241 |  |  | Transmital Date: 06/22/2023
[5 empty] | CRS No: NISOC-CRS-BK-BK14-PEDCO-110-CV-DW-0001_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | پیرو کامنت های 1 و 11، مستندات مورد اشاره در پاسخ پیمانکار در خصوص طرح پسماند ارائه گردد. |  | 1402-2294-169549 | 1402/04/31 | تاییدیه طرح پسماند در ضمائم نقشه قرار داده شده است. (در فایل زیر نیز قابل مشاهد است)
2 | جدول عملیات خاکی برای محوطه چاه و گودال آب و گل نیز ارائه شود. |  | 1402-2294-169549 | 1402/04/31 | جدول مورد نظر قرار داده شد. (در شیت شماره 19سمت راست بالا قابل مشاهده است)
طبق توافق صورت گرفته با سرپرست محترم سیویل مجموعه مجری (طرح نگهداشت و افزایش تولید ناحیه گچساران) نقشه، با وضعیت AFC ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: