## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-BK14-PEDCO-110-CV-PY-0001 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-2241 |  |  | Transmital Date: 22-JUN'-2023
Document Title : General Civil Layout - BK14 |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0001-CV-T-2241 |  |  | Transmital Date: 22-JUN'-2023
[5 empty] | CRS No: PEDCO-CRS-BK-GNRAL-PEDCO-110-CV-PY-0001-D05 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | کامنت های پتروایران |  | BK-SUR-ENG-CIV-02-08184 | 2023-07-26 | در فایل پیوست پاسخ داده شده است. (با Adobe Acrobat Reader ملاحظه کنید)
2 | کامنت های پتروایران |  | BK-SUR-ENG-CIV-02-08025 | 2023-07-02 | در فایل پیوست پاسخ داده شده است. (با Adobe Acrobat Reader ملاحظه کنید)
3 | کامنت های پتروایران |  | BK-SUR-ENG-CIV-02-08285 | 2023-08-20 | بر اساس هماهنگی ها اصلاحات مقتضی انجام شده است.
طبق توافق صورت گرفته با سرپرست محترم سیویل مجموعه مجری (طرح نگهداشت و افزایش تولید ناحیه گچساران- کارفرمای اصلی) نقشه، با وضعیت AFC ارسال می گردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: