## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W008N-PEDCO-110-CV-PY-0001_D00 |  |  |  |  | EPC Contractor Tr. No. : BK-HD-PEDCO-T-1773 |  |  | Transmital Date: 08-Jan-2023
Document Title:General Civil Layout -W008N |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-CV-T-1773 |  |  | Transmital Date: 08-Jan-2023
[5 empty] | CRS No: NISOC-CRS-BK-W008N-PEDCO-110-CV-PY-0001_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 |  |  | 1401/2294/468695 | 1401/12/08 | اعمال شد.
2 |  |  | 1401/2294/468695 | 1401/12/08 | طرح پسماند(چیدمان، ابعاد، احجام و پوشش گودالها) مطابق طرح تایید شده طراحی شده است.
3 |  |  | 1401/2294/468695 | 1401/12/08 | کدهای ارتفاعی مطابق با جلسه شفاف سازی برگزار شده با کارفرمای محترم درنظر گرفته شد.
4 |  |  | 1401/2294/468695 | 1401/12/08 | اعمال شد.
5 |  |  | 1401/2294/468695 | 1401/12/08 | اعمال شد.
6 |  |  | 1401/2294/468695 | 1401/12/08 | آبروهای جاده دسترسی نشان داده شد. در جاده سوخت تقاطعی با خط القعر موجود نیست.
7 |  |  | 1401/2294/468695 | 1401/12/08 | اعمال شد.
8 |  |  | 1401/2294/468695 | 1401/12/08 | تغییرات اندک جهت تطابق با توپوگرافی انجام شده است.
9 |  |  | 1401/2294/468695 | 1401/12/08 | جابجایی جاده انجام شد. شیب خاکریز در محدوده ورودی با شیب خاکریز لوکیشن ادغام شده و مطابق با شیب 2:3 خاکریزی انجام می گردد.
10 |  |  | 1401/2294/468695 | 1401/12/08 | اصلاح شد.
11 |  |  | 1401/2294/468695 | 1401/12/08 | اعمال شد.
12 |  |  | 1401/2294/468695 | 1401/12/08 | تراز اعلام شده مربوط به کف گودال 63.5 و تراز جاده پیرامون آن 67.5 است. در نقشه ها هم همین عدد در نظر گرفته شده است.
13 |  |  | 1401/2294/468695 | 1401/12/08 | اعمال شد.
14 |  |  | 1401/2294/468695 | 1401/12/08 | اعمال شد.
15 |  |  | 1401/2294/468695 | 1401/12/08 | اعمال خواهد شد.
16 |  |  | 1401/2294/468695 | 1401/12/08 | اعمال شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature
| Date: |  |  |  |  | Date: