## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0019 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2041 |  |  | Transmital Date:4/24/2022
Document Title:Process Data Sheets For Glycol Sump Drum |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2041 |  |  | Transmital Date: 4/24/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-DT-0019_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در مدرک P&id رویژن 6 خط مربوط به BLANKETING دو اینچ لحاظ شده است، این مهم در ویرایش پیشین همین مدرک نیز لحاظ شده بو و در این مدرک تغییر داده شده است لذا یکسان سازی با مدرک P&ID به عمل اید. |  | 1402/2294/158741 | 1402/04/24 | این مورد در دیتا شیت صحیح میباشد و در نسخه بعدی مدرک P&id اصلاح میگردد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: