## CRS
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-RT-0002 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2003 |  |  | Transmital Date: 4/8/2023
Document Title: Flare Radiation & Dispersion Study Report |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-2003 |  |  | Transmital Date: 4/8/2023
[5 empty] | CRS No:NISOC-CRS-BK-GCS-PEDCO-120-PR-RT-0002-D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در بخش 6 دو سناریوی Emergency & continouse flaring بر اساس Criteria مربوط به Total GS-SAF-253 بررسی گردد. |  | 1402-2294-112799 | 1402/03/24 | با توجه به مدرک Relief load summary موجود در بخش فرآیند، سناریو و یا توضیحاتی مبنی بر وجود continouse flaring وجود ندارد. لذا اصلاح و یا تکمیل گزارش بر اساس شرایط حاضر را نمیتوان برای این پروژه متصور بود.
2 | یکی از گازهای سمی حاصل از Flaring گاز SO2 میباشد و نه گاز سمی H2S لذا لازم است سناریو های بند فوق بر این اساس اصلاح گردد |  | 1402-2294-112799 | 1402/03/24 | با توجه به متن ارائه شده در GS-SAF-253(2012)Toal DEP در خصوص سناریوهایی که باید برای Flare مورد ارزیابی قرار گیرند اشاره به ارزیابی شرایط پراکنش سیال قابل احتراق و مواد سمی در زمان Flare flameout شده است که این موضوع نیز در گزارش منعکس شده است. در خصوص مطالعه پراکنش گاز SO2 ناشی از سوختن Flared gas این موضوع بررسی و به گزارش حاضر اضافه شد.
3 | حدود مواجه( TLV) گازهای سمی بر اساس مقادیر سازمان ACGIH بررسی شود. |  | 1402-2294-112799 | 1402/03/24 | در معیارهای ارائه شده این موضوع رعایت شده است
4 | لازم است در قسمت conclosion مدرک مقادیر Restricted area و Impacted area براساس سناریوی بررسی شده ذکر گردد. |  | 1402-2294-112799 | 1402/03/24 | هر چند موارد خواسته شد در جدول- 8 ارائه گردیده است اما جدول کامل آن در بخش Conclosion ارائه خواهد شد.
5 | لازم است کلیه اشکال مربوط به سناریوهای فوق به مدرک اضافه گردد. |  | 1402-2294-112799 | 1402/03/24 | موارد اعلام شده به گزارش جدید اضافه گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Maleki | Signature |  |  |  | Clarified By: | Signature
| Date: 19/04/2023 |  |  |  |  | Date: