## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-W007S-PEDCO-110-IN-TB-0005_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1905 |  |  | Transmital Date: 25 Feb 2023
Document Title: TBE/TBA For Control Valves - Extension of Binak B/C Manifold |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1905 |  |  | Transmital Date:25 Feb 2023
[5 empty] | CRS No: NISOC-CRS-BK-W007S-PEDCO-110-IN-TB-0005_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در خصوص سایز کنترل ولو ها و اطلاعات فرایندی مطابق دیتا شیت عمل گردد. |  | 1401-2294-498513 | ۱۴۰۱/۱۲/۲۸ | مشخصات فنی و فرآیندی کنترل ولوها منطبق بر PMR و نیازمندی های مربوطه خواهد بود.
2 | کلاس نشتی شیر ها مطابق Spec برابرV درنظرگرفته شود. |  | 1401-2294-498513 | ۱۴۰۱/۱۲/۲۸ | کلاس نشتی V برای شیرهای کنترلی درنظر گرفته میشود.
3 | قطعات یدکی علاوه بر ۲ ساله ،قطعات یدکی راه اندازی نیز در نظر گزفته شود. |  | 1401-2294-498513 | ۱۴۰۱/۱۲/۲۸ | 4- قطعات یدکی مربوطه (راه اندازی و دو ساله) مطابق با دستورالعمل تامین قطعات یدکی منضم به قرارداد فیمابین (پیوست 11) ارائه میگردد.
4 | پیرو بررسی متریال شیرآلات مشخص گردید متریال سازندگان دارای اختلاف است لذا اعلام میگردد تطابق مشخصات با PMS تاییدشده الزامی است. |  | 1401-2294-498513 | ۱۴۰۱/۱۲/۲۸ | تاییدیه سازندگان مبنی بر مطابقت با PMS پروژه به پیوست ارائه میگردد.
5 | لازم است تمام انحرافات بیان شده از سمت سازندگان قبل از عقد قرارداد نهایی گردد. |  | 1401-2294-498513 | ۱۴۰۱/۱۲/۲۸ | تاییدیه این مورد از سازنده منتخب اخذ ودر قرارداد منعکس خواهد شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 12 Mar 2023 |  |  |  |  | Date: