## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DG-0003_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1746 |  |  | Transmital Date: 31 Dec 2022
Document Title: ESD Level Hierarchy |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1746 |  |  | Transmital Date: 31 Dec 2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-DG-0003_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مدرک بر اساس نقطه نظرات ویرایش D01 مدرک ESD Block Diagram اصلاح گردد. |  | BK-SUR-ENG-INS-01-06696 | 2023-01-18 | نقطه نظرات ویرایش D01 مدرک ESD Block Diagram لحاظ شد. همچنین مدرک بر اساس آخرین رویژن P&ID به روز رسانی شد.
2 | تناقضات میان این مدرک و مدرک ESD Block Diagram، می بایست بر طرف گردد. به عنوان نمونه یکی از اثرات فعالسازی ESD-1A، روشن شدن Air Blower است که در مدرک ESD Level Hierarchy به Trip خوردن آن اشاره شده است. |  | BK-SUR-ENG-INS-01-06696 | 2023-01-18 | اصلاح شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 18 Jan 2023 |  |  |  |  | Date: