## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0002_D02 |  |  |  |  | EPC Contractor Tr. No.:BK-HD-PEDCO-T-1414 |  |  |  | Transmital Date: 9/19/2022
Document Title: PMR For GAS DEHYDRATION PACKAGE |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0109-ME-TR-1414 |  |  |  | Transmital Date: 9/19/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0002_D02 |  |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion | Clarification (By EPC Contractor)
QC comments :
1 | در بند 6: 1-عبارت "Project ITP Procedure(ITP For Mechanical Installation; Doc. No.BK-GNRAL-PEDCO-000-QC-PR-0009)" به "Commodity Procurement and Manufacturing Inspection Instruction" به شماره مدرك ICE-EID-MI-SP01-Rev.01 تغيير يابد. 2-دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات به شماره مدرك ICE-EID-MI-SP02-REV-01 اضافه گردد. |  | BK-SUR-ENG-MEC-01-05749 | 2022-09-24 | اعمال گردید. |  |  | See item No. 4 | اعمال گردید.
2 | در جدول Attachment 1(List of Reference/Applicable Documents): 1-دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات به شماره مدرك ICE-EID-MI-SP02-REV01 اضافه گردد. |  | BK-SUR-ENG-MEC-01-05749 | 2022-09-24 | اعمال گردید. |  |  | Closed
3 | در جدول Attachments 2 (Vendor Documents Minimum Requirements): 1. در رديف 1، عبارت "See Attachment 2" حذف گردد. 2- عبارت "List of Documents will be Finalized in VDLS" به عنوان نوت اضافه گردد |  | BK-SUR-ENG-MEC-01-05749 | 2022-09-24 | اعمال گردید. |  |  | See item No. 8 | اعمال گردید.
4 | جهت يكسان سازي در كليه مدارك MR پروژه، نگارش توضيحات بند6 مطابق ذيل انجام گردد. |  | BK-SUR-ENG-MEC-02-08204 | 2023-08-01 | اعمال گردید. |  |  |  | اعمال گردید.
The equipment shall be inspected and tested in accordance with the Inspection &Test plan (ITP) issued by the vendor and approved by the CLIENT and EPC/EPD CONTRACTOR before the award of the order . The Inspection & Test plan (ITP ) shall be at least according to the Commodity Procurement and Manufacturing Inspection Instruction ( Docs .Nos. ICE-EID-MI-SP01-Rev01) , Inspection Level of Commodity and Equipment ( Docs .Nos. ICE-EID-MI-SP02-Rev01) and Data Sheets. The vendor shall in any case conduct all the tests required by contractual documents, specifications, codes and standards, manufacturer standard quality system and keep the relevant documentation. All required manufacturing and function test/inspection also Factory Acceptance Test /Site Acceptance Test and Quality Assurance requirements shall be considered in vendor responsibility as per project specification.
5 | لغت ''Purchaser" بايستي در قسمت General Definition تعريف گردد. |  | BK-SUR-ENG-MEC-02-08204 | 2023-08-01 | اعمال گردید. |  |  |  | اعمال گردید.
6 | جهت يكسان سازي، لغت Supplier در متون به Vendor تغيير يابد. |  | BK-SUR-ENG-MEC-02-08204 | 2023-08-01 | اعمال گردید. |  |  |  | اعمال گردید.
7 | در جدول Attachment 1(List of Reference/Applicable Documents): در رديف General Document & Procedures ، شماره مدرك بصورت صحيح E&C-QC-SP-1 ذكر گردد. |  | BK-SUR-ENG-MEC-02-08204 | 2023-08-01 | اعمال گردید. |  |  |  | اعمال گردید.
8 | در جدول Attachments 2(Vendor Documents Minimum Requirements): 1. Painting Operator Qualification Record اضافه گردد. 2- SAT Procedure اضافه گردد. |  | BK-SUR-ENG-MEC-02-08204 | 2023-08-01 | اعمال گردید. |  |  |  | اعمال گردید.
Mechanical comments :
1 | اطلاعات لازم در خصوص UCP , LCP و ANALYZER اين پكيج در مدرك قيد گردد. |  | BK-SUR-ENG-MEC-02-08204 | 2023-08-01 |  |  |  |  | اعمال گردید.
2 | با توجه به عدم ارسال اين مدرك به ذينفع اصلي پروژه ، لازم است پس از اعمال نظرات ، نسبت به جايگزيني اين مدرك (بدون تغيير ويرايش) بر روي همين ترانسميتال اقدام گردد. |  | BK-SUR-ENG-MEC-02-08204 | 2023-08-01
3 | اطلاعات لازم در خصوص Analyzer اين پكيج در بخش Scope of supply اين مدرك درج گردد. |  | BK-SUR-ENG-MEC-02-08283 | 2023-08-15 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: H.Ghadyani | Signature | M.Fakharian
Date: 8/15/2023