## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0002_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1414 |  |  | Transmital Date: 19-Sep-2022
Document Title: PMR For GAS DEHYDRATION PACKAGE |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0109-ME-TR-1414 |  |  | Transmital Date: 19-Sep-2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-MR-0002_D02 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ساختار کلی مدرک مورد تایید بوده و لیکن ارسال نسخه بعدی این مدرک منوط به نهایی سازی مدارک مرتبط مهندسی ودرج نسخه تایید شده در مدارک است. |  | 1401/2294/249364 | 1401/07/13 | ا توجه به تایید بیشتر مدارک پیوست 1 و عدم وجود نقطه نظر کلیدی بر مدارک ضمیمه MR ، لذا از کارفرمای محترم خواهشمند است جهت تسریع در امور خرید، بررسی مدرک در دستور کار آن کارفرمای محترم قرار گیرد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.bavarsad | Signature |  |  |  | Clarified By: | Signature
Date: 24/09/2022