## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GNRAL-PEDCO-220-HV-PY-0002-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0938 |  |  | Transmital Date: 14/MAY/2022
Document Title: HVAC System Layout |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-HV-TR-0938 |  |  | Transmital Date: 14/MAY/2022
[5 empty] | CRS No: NISOC-CRS-BK-GNRAL-PEDCO-220-HV-PY-0002_D00 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نقشه ها مطابق با آخرین ویرایش نقشه های معماری اصلاح و ارسال گردد.(Space 102) |  | 1400/2294/92177 | 1401/03/17 | اعمال گردید.
2 | سیستم سرمایش و تهویه جهت فضای 110 (kitchen) در نظر گرفته شود. |  | 1400/2294/92177 | 1401/03/17 | اعمال گردید.
3 | نقشه های مربوط به کمپ پیمانکاران از مدرک حذف گردد. |  | 1400/2294/92177 | 1401/03/17 | اعمال گردید.
4 | لیست فضاها در نقشه اظافه گردد. (Space tag NO) (کلیه صفحات) |  | 1400/2294/92177 | 1401/03/17 | اعمال گردید.
5 | تهویه فضای شماره 9 مورد بازنگری قرار گیرد. (در حمام های فضای مذکور فن تعبیه گردد) |  | 1400/2294/92177 | 1401/03/17 | جهت فضاهای مذکور فن تخلیه هوا در نظر گرفته شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.Behbahani | Signature | H.Naserizadeh |  |  | Clarified By: K.Ahmadi | Signature | M.Fakharian
| Date: 06/29/2022 |  |  |  |  | Date: 07/26/2023