## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-CN-0005 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1872 |  |  | Transmital Date: 15/02/2023
Document Title: Calculation Note For Line Sizing |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-PR-TR-1872 |  |  | Transmital Date: 15/02/2023
[5 empty] | CRS No: CRS-BK-GCS-PEDCO-120-PR-CN-0005-D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | فایل های محاسباتی Excel مربوط بهخطوط نیتروژن در Tab-Calculation(UTILITY 2) اصلاح شده و موارد خطا برطرف گردد. |  | BK-SUR-ENG-PCS-01-07046 | 2023-02-15 | اعمال گردید.
2 | Sizing خط 6 اینچ Closed drain Header در مدرک ارائه گردد. |  | BK-SUR-ENG-PCS-01-07046 | 2023-02-15 | با توجه به اینکه این خط به صورت مداوم در سرویس نخواهد بود،سایز خط هدر CLOSE DRAIN بر اساس محدودیتهای شیب و به علت بالا بودن سطح ابهای زیر زمینی و اسناد مهندسی پایه و همچنین جهت جلوگیری از BLOCKAGE در خط لوله زیر زمینی حد اقل6 اینچ انتخاب شده است. و سایزینگی برای آن نمیتوان ارائه داد. این نقطه نظر در نسخه های پیشین مدرک نیز قابل ارائه بوده است ولی در نسخه D03 به عنوان کامنت جدید محسوب میشود.
3 | ضروريست نقطه نظرات ذينفع اصلي در خصوص اين مدرك اعمال گردد. |  | BK-SUR-ENG-PCS-01-07046 | 2023-02-15 | اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.Maleki | Signature |  |  |  | Clarified By: | Signature
| Date: 28/02/2023 |  |  |  |  | Date: