## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-DT-0001_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1881 |  |  | Transmital Date: 2/19/2023
Document Title: Data Sheets For Strainers |  |  |  |  | NISOC Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-1881 |  |  | Transmital Date:2/19/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PI-DT-0001_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | همانگونه که در نامه شماره 01/2294/156732 مورخ 1401/05/05 بیان گردید،با توجه به عدم تایید مطالعات خوردگی در خصوص جنس کالا و میزان خوردگی مجاز نمی توان اظهارنظر نمود. |  | 1402/2294/3720 | 1402/01/07 | آخرین ویرایش مدرک مطالعات خوردگی ارسال شده است.
2 | موارد مطروحه در ویرایش پیشین مدرک(نامه شماره01/2294/156732 مورخ 1401/05/05)میبایست اصلاح گردد.همچنین کلیه تغییرات ویرایش جدید نسبت به ویرایش قبل میبایست با نشان ویرایش در مشخص گردد. |  | 1402/2294/3720 | 1402/01/07 | نفطه نظر کافرمای محترم اعمال می گردد.
3 | استاندارد ASME SEC VIII و همچنین نقشه شماره IPS-D-PI-114،IPS-D-PI-113 و دستورالعمل بازرسی خرید و ساخت کالای مناطق نفتخیز جنوبICE-EID-MI-SP01-REV01 به قسمت مراجع افزوده شود. |  | 1402/2294/3720 | 1402/01/07 | نفطه نظر کافرمای محترم اعمال می گردد.
4 | جنس Screen و اجزا داخلی حداقل معادل تریم شیرآلات همان کلاس انتخاب شود. |  | 1402/2294/3720 | 1402/01/07 | نفطه نظر کافرمای محترم اعمال می گردد. در تریم شیرآلات بالاترین متریال SS316L می باشد که برای تمامی فیلترها در نظر گرفته شده است.
5 | الزامات دستورالعمل بازرسی خرید و ساخت کالای مناطق نفتخیز جنوب ICE-EID-MI-SP01-REV01 در بازرسی رعایت گردد. |  | 1402/2294/3720 | 1402/01/07 | نفطه نظر کافرمای محترم اعمال می گردد.
6 | اظهار نظر نهایی در خصوص جنس کالا پس از نهایی سازی PMS میسر خواهد بود. |  | 1402/2294/3720 | 1402/01/07 | آخرین ویرایش مدرک PMS ارسال شده است.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 2/27/2023 |  |  |  |  | Date: 1402/04/21