## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-MR-0004_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1306 |  |  | Transmital Date: 23 Aug 2022
Document Title: PMR For On/off & Shutdown Valves |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1306 |  |  | Transmital Date: 23 Aug 2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-MR-0004_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي مي باشد. |  | BK-SUR-ENG-INS-01-05631 | 2022-09-12 | ملاحظه گردید.
2 | Min Requirement ها براي ITP در مدرك آورده شود. (Monitoring/Review/witness) |  | BK-SUR-ENG-INS-01-05631 | 2022-09-12 | طبق توافقات صورت گرفته با کارفرمای محترم جدولITP از فروشنده منتخب برای خرید تجهیزات ،دریافت و به کارفرما برای بررسی و اعلام نظر ارسال می گردد لذا جدول ITP در این مدرک ارائه نمی گردد.
3 | Quality Control Plan (QCP) بر اساس مدارك پروژه مشخص شود. |  | BK-SUR-ENG-INS-01-05631 | 2022-09-12 | در بند 6 آورده شده است.
4 | براي Trace راحت تر مدرك در يكي از ضمايم، مسئوليت هاي مربوط به Vendor و Purchaser مشخص شود. |  | BK-SUR-ENG-INS-01-05631 | 2022-09-12 | مدرک مطابق فرمت یکسان برای PMR های پروژه تهیه شده است. بخش مربوط به مسئولیت سازنده دیده شده است.
5 | در صورتي كه مدارك پيش نياز مانند ديتاشيت و .... تاييد و نهايي نيست و داراي كامنت اساسي مي باشد MR نهايي نمي باشد. |  | BK-SUR-ENG-INS-01-05631 | 2022-09-12 | ملاحظه گردید.
6 | موارد مربوط به Actuator و Accessories در مدرك اضافه گردد. |  | BK-SUR-ENG-INS-01-05631 | 2022-09-12 | در قالب نوت اضافه گردید.
7 | Attachment-2 بر اساس نياز Valve بروز رساني گردد. |  | BK-SUR-ENG-INS-01-05631 | 2022-09-12 | بروز رسانی گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 3 sep 2022 |  |  |  |  | Date: