## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-LD-0002_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1067 |  |  | Transmital Date: 12 Jun 2022
Document Title: ESD Logic Diagram |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1067 |  |  | Transmital Date: 12 Jun 2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-LD-0002_D00 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | موارد بر اساس آخرين نتايج به دست آمده در جلسات HAZOP و SIL مجددا مورد بازنگري قرار گيرد. |  | BK-SUR-ENG-INS-01-05037 | 2022-07-09 | ملاحظه شد.
2 | تمام مدارك وابسته مانند Hairaricy ، ESD I/O List و ESD C&E بايد با هم منطبق باشد. |  | BK-SUR-ENG-INS-01-05037 | 2022-07-09 | ملاحظه شد.
3 | با توجه به اختلاف در سطوح shutdown در مدرك ESD Philossophy و كامنت هاي مطرح شده در ESD Hararicy، موارد در اين مدرك اعمال شود. |  | BK-SUR-ENG-INS-01-05037 | 2022-07-09 | اصلاح شد.
4 | كليه مسئوليت در خصوص اين مدرك از نظر مالي و زماني بر عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-05037 | 2022-07-09 | ملاحظه شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 9 Jul 2022 |  |  |  |  | Date: