## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-DC-0002_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0931 |  |  | Transmital Date: 11 May 2022
Document Title: Instrument & Control System Design Criteria |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-0931 |  |  | Transmital Date: 11 May 2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-DC-0002_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | در پاسخ به Reply sheet: ۱- مورد ۴ به قوت خود باقی است.( اعلام گردد تمامی Work station ها ، شامل Mouse, key board, Monitor و... Industrial type میباشد. |  | 1401/2294/92293 | 1401/03/17 | مطابق خواست کارفرمای محترم اصلاح شد.
2 | دیگر موارد نظر خاصی مطرح نمیباشد. |  | 1401/2294/92293 | 1401/03/17 | -
3 | با توجه به اینکه عبارت Owner در مدرک تعریف نشده است از عبارت جایگزین Client استفاده شود. |  | 1401/2294/92293 | 1401/03/17 | مطابق خواست کارفرمای محترم اصلاح شد.
4 | مانیتورها ۳۲ اینچ میباشد. اصلاح لازم در مدرک صورت پذیرد. |  | 1401/2294/92293 | 1401/03/17 | مطابق خواست کارفرمای محترم اصلاح شد.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 28 May 2022 |  |  |  |  | Date: