## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-LI-0008 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2133 |  |  | Transmital Date: 7/24/2023
Document Title: Relief Load Summery |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-2133 |  |  | Transmital Date: 7/24/2023
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-PR-LI-0008_D05 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | به روز رسانی اطلاعات فرایندی با آخرین ویرایش مدارک P&id و PFD انجام گردد. به عنوان مثال میتوان به دمای قید شده برای V-2104 اشاره کرد. |  | 1402-2294-137957 | 1402/04/10 | کلیه اطلاعات بر اساس آخرین ویرایش مدارک به روز رسانی شده است
2 | اطلاعات فرایندی میبایست با آخرین صورتجلسه بررسی مدارک مورخ 22/03/1402 بروزرسانی گردد. به عنوان مثال میتوان به اطلاعات فرایندی V-2101 اشاره کرد. |  | 1402-2294-137957 | 1402/04/10 | کلیه اطلاعات بر اساس آخرین ویرایش مدارک به روز رسانی شده است
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: 24/08/2021