## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PI-DT-0005_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1958 |  |  | Transmital Date: 13/MAR/2023
Document Title: Data Sheets For Piping Insulation Joints |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-1958 |  |  | Transmital Date: 13/MAR/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PI-DT-0005_D01 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظرات بصورت مارك شده در مدرك به پيوست ارسال مي گردد. |  | BK-SUR-ENG-PIP-01-04774 | 2022-06-20 | احتراما موارد مارک شده اعمال گردید.
2 | نظرات بصورت مارك شده در مدرك به پيوست ارسال مي گردد. |  | BK-SUR-ENG-PIP-01-07208 | 2023-03-14 | احتراما موارد مارک شده اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: F.Amiri | Signature |  |  |  | Clarified By: S.Faramarzpour | Signature
| Date: 14/03/2023 |  |  |  |  | Date: 14/03/2023