## QA-QC
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No:BK-W018S-PEDCO-110-PI-MR-0005_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1349 |  |  | Transmital Date: 9/4/2022
Document Title: PMR FOR GASKETS– W018S |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PI-TR-1349 |  |  | Transmital Date: 9/4/2022
[5 empty] | CRS No: NISOC-CRS-BK-W018S-PEDCO-110-PI-MR-0005_D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | ساختار کلی مدرک مورد تایید بوده ولیکن ارسال نسخه بعدی مدارک فوق منوط به نهایی سازی مدارک مرتبطه مهندسی و درج نسخ تایید شده(AFC) است.معذالک جهت پرهیز از مکاتبات مضاعف و تسریع در تایید مدارک فوق،نهایی سازی مدارک پیش نیاز(که در پیوست 1 مدرک اشاره شده است)در دستور کار تیم مهندسی آن پیمانکار قرار گیرد. |  | 1401/2294/249366 | 1401/07/13 | احتراما نقطه نظر اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: | Signature | M.Fakharian
| Date: |  |  |  |  | Date: