## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-LI-0007 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1692 |  |  | Transmital Date: 12/12/2022
Document Title: I&C Power Consumption Summary |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1692 |  |  | Transmital Date: 12/12/2022
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-IN-LI-0007_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به عدم ارسال جزئیات و مشخص نبودن مرجع محاسبات بار سیستم های کنترل ، اظهار نظر امکان پذیر نمی باشد خاطر نشان می سازد تاکنون چندین بار مدرک به همین صورت کلی و فاقد مبنای طراحی ارسال گردید. و از آنجایی که این مدرک پیش نیاز محاسبات مدارک بخش برق ( UPSو باطری شارژر) و بخش سیویل بوده بایستی در الویت کاری قرار گیرد تا با ارائه جزئیات و مبانی طراحی امکان نهایی سازی مدارک مرتبط فراهم گردد |  | 1401/2294/380517 | 1401/10/09 | محاسبات بار مصرفی سیستم های کنترل با توجه به برند زینمس مجددا طراحی گردید. تعداد I/O ها و همه متعلقات در پنل سیستم و مارشالینگ به تفکیک در پیوست Aو B ذکر گردیده است. ;کاتالوگ های مبنای محاسبات به پیوست ارسال میگردد.
موارد MOM ضمیمه شماره نامه 1402-2291-167106 اعمال گردید.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 08 May 2022 |  |  |  |  | Date: