## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-IN-LI-0007_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1692 |  |  | Transmital Date: 12 Dec 2022
Document Title: I&C Power Consumption Summary |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-IN-TR-1692 |  |  | Transmital Date: 12 Dec 2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-IN-LI-0007_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق بند 13 شرايط عمومي پيمان في مابين و با توجه به مسئوليتهاي كامل مالي/قراردادي پيمانكار, مسئوليت بروز هرگونه اشتباه و تناقض, كمبود اسناد و مدارك فني و اطلاعات تهيه شده توسط پيمانكار, اعم از اينكه از سوي كارفرما تاييد شده يا نشده باشد, به عهده پيمانكار فرعي (هيرگان) مي باشد. |  | BK-SUR-ENG-INS-01-06556 | 2022-12-28 | ملاحظه گردید
2 | با توجه به نهايي نبودن مدارك پيش نياز مانند I/O در صورت تغيير موارد در اين مدرك در نظر گرفته شود. |  | BK-SUR-ENG-INS-01-06556 | 2022-12-28 | با توجه به آخرین نسخه مدارک I/O لیست DCS / ESD / F&G محاسبات بروز رسانی گردید.
2 | ميزان بار مصرفي ارائه شده در اين پروژه، براي 110 VAC با تجارب اين امور هم خواني ندارد و به نظر زياد مي باشد، لذا مستندات لازم در خصوص محاسبات بار مصرفي ارائه گردد. لازم به ذكر است كه اين مدرك بعد از نهايي شدن مدارك سازنده پكيج ها و سيستم كنترل قابل بررسي نهايي خواهد بود. |  | BK-SUR-ENG-INS-01-06556 | 2022-12-28 | محاسبات با توجه تعداد I/O ها و تجهیزات موجود ( مصرف کننده ) در پنل های مارشالینگ و سیستم مجددا طراحی گردید لازم به ذکر است مبنای طراحی برند زینمس می باشد. در پیوست A و B مدرک به تفکیک پنل مارشالینگ و سیستم تجهیزاتی که نیاز به مصرف دارند ذکر شده است.
2 | در خصوص سطر 5 از صفحه 4، مشخص شود كه تعداد پنل ها و نوع پيكربندي آنها به چه صورت است. بطور واضح مشخص شود كه سه unit در نظرگرفته شده است. |  | BK-SUR-ENG-INS-01-06556 | 2022-12-28 | اصلاح گردید
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: S.Akbari | Signature |  |  |  | Clarified By: | Signature
| Date: 28 Dec 2022 |  |  |  |  | Date: