## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-EL-CN-0004_D03 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1625 |  |  | Transmital Date: 28-Nov-2022
Document Title: Calculation Note For Lighting System of Well Pads Area |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0109-EL-TR-1625 |  |  | Transmital Date: 28-Nov-2022
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-EL-CN-0004_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | پیرو نامه 102561 مورخ 1401/10/07 دریافتی از گچساران، مقتضی است، نسبت به اصلاح مدرک اقدام گردد. در این خصوص لازم است، روشنایی تمام تجهیزات و محوطه سر چاهی و محوطه سر چاهی از جمله روشنایی فنس محوطه چاه نیز تامین گردد. |  | 1401-2290-402431 | 1401-10-24 | با توجه به درخواست آن کارفرمای محترم مبنی بر استفاده از پایه های روشنایی بیشتر در محوطه تسهیلات سرچاهی، تعداد پایه ها به 4 عدد افزایش یافت. لازم به ذکر است در مطالعات بیسیک دو عدد در نظر گرفته شده است.
2 | پس از نهایی شده مدرک Layout و محاسبات سیستم روشنایی جهت طرح موضوع در کمیته تغییرات نسبت به تهیه فرم تغییر کار (فرم C/R) اقدامات لازم را بعمل آورید. |  | 1401-2290-402431 | 1401-10-24
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC ContractorS24:AF29
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 11-Dec-22 |  |  |  |  | Date: