## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-PR-DT-0021 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1586 |  |  | Transmital Date: 11/14/2022
Document Title: Process Data Sheets For Glycol Transfer Pumps |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-PR-TR-1586 |  |  | Transmital Date: 11/14/2022
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-PR-DT-0021_D03 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | نظری مطرح نمی باشد. شایان ذکر است که مطابق شرایط عمومی پیمان فی مابین و با توجه به مسئولیتهای مالی-قراردادی پیمانکار، مسئولیت بروز هرگونه اشتباه و تناقض، کمبود اسناد و مدارک فنی و اطلاعات تهیه شده از سوی پیمانکار اعم از اینکه از سوی کارفرما تایید شده و یا نشده باشد بر عهده پیمانکار است. شایان ذکر است با توجه به عدم دريافت اطلاعات از سازنده پكيج نمزدا، صحت فشار مقصد و ارتفاع آن براي پمپ 2103 بر عهده پيمانكار بوده و هر گونه تغيير در اطلاعات (توسط سازنده پكيج نمزدا) بدون هيچ گونه ادعايي مي بايست در نظر گرفته شود. |  | BK-SUR-ENG-PCS-01-06307 | 2022-11-30 | مورد تایید است.
2 | ضروریست نقطه نظرات ذینفع اصلی پروژه در خصوص ترنسمیتال 1373 بخش مکانیک، در خصوص این پمپ مد نظر قرار گرفته و یا پاسخ مقتضی در این خصوص برای ایشان، ارسال گردد. |  | BK-SUR-ENG-PCS-01-06307 | 2022-11-30 | بروی ترنسمیتال فوق در خصوص این مدرک نقطه نظری مطرح نگردیده است
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: | Signature |  |  |  | Clarified By: M.Fakharian | Signature
| Date: |  |  |  |  | Date: