## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-SSGRL-PEDCO-110-EL-DT-0004_D04 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-2113 |  |  | Transmital Date: 15-May-2023
Document Title: Data Sheets For Diesel Generator of Well Pads |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0202-EL-TR-2113 |  |  | Transmital Date: 15-May-2023
[5 empty] | CRS No: NISOC-CRS-BK-SSGRL-PEDCO-110-EL-DT-0004_D04 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | مطابق با بند 2 از نامه شماره 1402-2294-13121 مورخ 1402-01-18 در صورتیکه ظرفیت برآورد شده تجهیزات کمتر از ظرفیت قید شده در اسناد پیمان باشد، ظرفیت موجود در اسناد پیمان ملاک عمل قرار گیرد. لذا مقتضی است مدرک بر این اساس اصلاح و برای این امور ارسال گردد. |  | 1402-2294-86534 | 1402-03-07 | مدرک لیست بار و محاسباتی دیزل ژنراتور سرچاهی به ترتیب با شماره ترسنمیتال 1649 و 1772 توسط آن کارفرمای محترم مورد تأییدِ نهایی قرار گرفته است. لذا فقط در مدرک داده برگه دیزل ژنراتور ظرفیت از 198.5 کیلوولت آمپر به عدد 250 کیلوولت آمپر افزایش یافته که در این ترنسمیتال آورده شده است. لازم به ذکر است پس از عقد قرارداد با سازنده، وندور می بایست مدرک محاسباتی دیزل ژنراتور را تولید و به روزرسانی کند.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: H.Mozafari | Signature |  |  |  | Clarified By: | Signature
| Date: 29-May-2023 |  |  |  |  | Date: