## QAQC
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No. : BK-SSGRL-PEDCO-110-ME-MR-0001_D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1733 |  |  |  | Transmital Date: | 28.Dec.2022
Document Title: PMR FOR FUEL OIL STORAGE DRUM OF WELL PADS |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-1733 |  |  |  | Transmital Date: | 28.Dec.2022
[5 empty] | CRS No: PEDCO-CRS-BK-SSGRL-PEDCO-110-ME-MR-0001_D00 |  |  |  | CRS Status: ‍
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Brief Action | Client Conclusion
1 | ساختار کلی مدرک مورد تایید بوده ولیکن ارسال نسخه بعدی مدارک فوق منوط به نهایی سازی مدارک مرتبط مهندسی و درج نسخه تایید شده (AFC) است. معذالک جهت پرهیز از مکاتبات مضاعف و تسریع در تایید مدارک فوق، نهایی سازی مدارک پیشنیاز (که در پیوست 1 مدرک اشاره شده است) در دستور کار تیم مهندسی آن پیمانکار قرار گیرد. |  | 1401/2294/423455 | 1401/11/05 | تغییرات اعمال شده در مدرک مطابق با نقطه نظرات شرکت PEDCO می باشد که به پیوست تقدیم می شود.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M. Torkaman | Signature |  |  |  | Clarified By: | Signature
| Date: 01/22/2023 |  |  |  |  | Date: