## QAQC
N.I.S.O.C |  | Binak Project
COMMENT & REPLY SHEET
Document No. : BK-SSGRL-PEDCO-110-ME-MR-0001-D00 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1733 |  |  |  | Transmital Date:12/28/2022
Document Title: PMR FOR FUEL OIL STORAGE DRUM OF WELL PADS |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-1733 |  |  |  | Transmital Date:12/28/2022
[5 empty] | CRS No: PEDCO-CRS-BK-SSGRL-PEDCO-110-ME-MR-0001_D00 |  |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Brief Action | Client Conclusion
1 | در بند 12.2، حضور نمایندگان شرکتهای PEDCO و NISOC نیز در جلسه PIM الزامی میباشد. همچنین سازنده میبایست مدارک ITP, QCP و MPS را قبل از برگزاری جلسه PIM جهت بررسی ارائه نماید. |  | BK-SUR-ENG-MEC-01-06735 | 2023-01-22 | نقطه نظر کارفرمای محترم اعمال شد.
2 | عبارت زیر در انتهای پیوست 2 اضافه گردد: "List of documents will be finalized in vendor document index and schedule" |  | BK-SUR-ENG-MEC-01-06735 | 2023-01-22 | نقطه نظر کارفرمای محترم اعمال شد.
3 | در بند 9، زمان گارانتی تجهیز 18 ماه پس از تحویل یا 12 ماه پس از راه اندازی هر کدام که زودتر اتفاق افتد در نظر گرفته شود. |  | BK-SUR-ENG-MEC-01-06735 | 2023-01-22 | نقطه نظر کارفرمای محترم اعمال شد.
4 | در بند 12.2، زمان ارائه مدارك QCP, ITP , MPS، قبل از برگزاري جلسه PIM درج گردد. |  | BK-SUR-ENG-MEC-02-07836 | 2023-06-10 | نقطه نظر کارفرمای محترم اعمال شد.
5 | در جدول Attachment 1 قسمت General Documents عنوان مدرك بصورت صحيح " دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات " آورده شود. |  | BK-SUR-ENG-MEC-02-07836 | 2023-06-10 | نقطه نظر کارفرمای محترم اعمال شد.
6 | جهت يكسان سازي در كليه مدارك MR پروژه، نگارش توضيحات بند6 مطابق ذيل انجام گردد. |  | BK-SUR-ENG-MEC-02-07836 | 2023-06-10 | نقطه نظر کارفرمای محترم اعمال شد.
7 | The equipment shall be inspected and tested in accordance with the Inspection &Test plan (ITP) issued by the vendor and approved by the CLIENT/EPC&EPD CONTRACTOR before the award of the order . The Inspection & Test plan (ITP ) shall be at least according to the Commodity Procurement and Manufacturing Inspection Instruction ( Docs .Nos. ICE-EID-MI-SP01-Rev01) , Inspection Level of Commodity and Equipment ( Docs .Nos. ICE-EID-MI-SP02-Rev01) and Data Sheets. The vendor shall in any case conduct all the tests required by contractual documents, specifications, codes and standards, manufacturer standard quality system and keep the relevant documentation. All required manufacturing and function test/inspection also Factory Acceptance Test /Site Acceptance Test and Quality Assurance requirements shall be considered in vendor responsibility as per project specification. |  | BK-SUR-ENG-MEC-02-07836 | 2023-06-10
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M. Torkaman | Signature H.Naserizadeh |  |  |  | Clarified By: H.Ghadyani | Signature | M.Fakharian
| Date: 06/10/2023 |  |  |  |  | Date: