## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0016_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0406 |  |  | Transmital Date: 12/29/2021
Document Title: Mechanical Data Sheets For Lean Glycol Storage Tank |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-0406 |  |  | Transmital Date: 12/29/2021
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-BK-GCS-PEDCO-120-ME-DT-0016_D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | با توجه به اینکه محاسبات طراحی ارسال نشده است، ضروزی است معیار تعیین حداقل ضخامتها در مدرک مشخص گردد. در ضمن چنانچه در این زمینه محاسبات اولیه صورت گرفته است ارایه آن ضرورت دارد. |  | 1400/2294/352427 | 16/10/1400 | معیار و مبنای طراحی تانک مربوطه ، استاندارد API 650 و IPS می باشد که در سطر 41 صفحه 4 داده برگ فنی، ازایه شده است. با توجه به نهایی شدن ضخامت ها توسط سازنده، لذا اطلاعات درخواستی در مدارک سازنده ارایه خواهد شد.
2 | مقیاس نقشه مندرج در مدرک رعایت نشده است. |  | 1400/2294/352427 | 16/10/1400 | مقیاس ارایه شده در نقشه، Not To Scale می باشد.
3 | تعیین میزان C.A. پس از انجام مطالعات خوردگی امکانپذیر خواهد بود. |  | 1400/2294/352427 | 16/10/1400 | با توجه به عدم دریافت نقطه نظرخاصی از طرف کارفرمای محترم بر تانک مذکور در مدرک مطالعات خوردگی، لذا میزان خوردگی اعلام شده در مدرک داده برگ فنی صحیح می باشد.
4 | الزام سازنده به ارایه کتابچه محاسبات و مدارک طراحی به عنوان یادداشت ذکر گردد. |  | 1400/2294/352427 | 16/10/1400 | نقطه نظرات کارفرمای محترم در Note 27 اعمال شد.
5 | اطلاعات فرآیندی مطابق با آخرین ویرایش مدارک مربوطه لحاظ گردد. |  | 1400/2294/352427 | 16/10/1400 | نقطه نظرات کارفرمای محترم مد نظر قرار گرفت.
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: P.BAVARSAD | Signature | H.naserizadeh |  |  | Clarified By: | Signature | M.Fakharian
| Date: 1/26/2022 |  |  |  |  | H.Ghadyani