## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-DT-0016_D01 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-0406 |  |  | Transmital Date: 12/29/2021
Document Title: Mechanical Data Sheets For Lean Glycol Storage Tank |  |  |  |  | PEDCO Tr. No.:BK-PEDCO-NISOC-0005-ME-TR- 0406 |  |  | Transmital Date: 12/29/2021
[5 empty] | CRS No: NISOC-CRS-BK-GCS-PEDCO-120-ME-DT-0016_D01 |  |  | CRS Status:
| Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | please find the atatched commets |  | BK-SUR-ENG-MEC-00-02824 | 2022-01-26 | There is No. Comment in attached file.
1 | please find the atatched commets |  | BK-SUR-ENG-MEC-02-07880 | 2023-06-14 | Please find the reply on attachment.
2 | مرجع پارامترهاي لرزه اي - ضرايب اهميت در جدول صحيح كنترل و ارائه گردد.رفرنس ضرايب بر مبناي گزارش مطالعات زلزله-ژئوتكنيك كنترل و اشاره شود، مباني آيين نامه اي مورد توافق با كارفرما براي منظور شدن سرعت باد كنترل و اعلام شود. |  | BK-SUR-ENG-MEC-02-07880 | 2023-06-14 | نقطه نظرات کارفرمای محترم مطابق توافق صورت گرفته در جلسه مورخ 5.06.1402 اعمال شد.
3 | از آنجا كه مدرك به كارفرما ارسال نشده ، پس از اعمال نظرات بالا نسبت به جايگزيني اين مدرك بر روي همين ترانسميتال اقدام نماييد. |  | BK-SUR-ENG-MEC-02-07880 | 2023-06-14
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: Ah.behbahani | Signature | H.naserizadeh |  |  | Clarified By: H.Ghadyani | Signature | M.Fakharian
Date: 6/14/2023