## Sheet1
N.I.S.O.C |  | Binak Project
COMMENT REPLY SHEET
Document No: BK-GCS-PEDCO-120-ME-MR-0006_D02 |  |  |  |  | EPC Contractor Tr. No.: BK-HD-PEDCO-T-1885 |  |  | Transmital Date: 2/20/2023
Document Title: PMR For Instrument/Plant Air & Nitrogen Packages |  |  |  |  | PEDCO Tr. No.: BK-PEDCO-NISOC-0005-ME-TR-1885 |  |  | Transmital Date: 2/20/2023
[5 empty] | CRS No: PEDCO-CRS-BK-GCS-PEDCO-120-ME-MR-0006_D02 |  |  | CRS Status:
Item | Comments (NISOC/PEDCO) |  | Email/letter No. | Comment Date | Clarification (By EPC Contractor) |  |  | Client Conclusion
1 | اين ترانسميتال به ذينفع اصلي ارسال نگرديد.پس از اعمال نظرات در مدرك نسبت به جايگزين كردن مدرك اقدام نماييد. |  | BK-SUR-ENG-MEC-02-08303 | 2023-08-20 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته است
2 | اين ترانسميتال به ذينفع اصلي ارسال نگرديد.پس از اعمال نظرات در مدرك نسبت به جايگزين كردن مدرك اقدام نماييد. |  | BK-SUR-ENG-MEC-02-07573 | 2023-10-05 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته است
QC/QA COMMENTS:
1 | در بند 5.1.1: -عبارت "QA Organization" به "QA/QC Organization Chart" تغيير يابد. |  | BK-SUR-ENG-MEC-01-07139 | 2023-03-07 | Noted
2 | در بند 6: -عبارت "QC Plan" و "Quality Control Plan" به "Inspection and Test Plan (ITP)" تغيير يابد. -دستورالعمل انتخاب سطح بازرسي كالا و تجهيزات به شماره مدرك ICE-EID-MI-SP02-REV-01 اضافه گردد. |  | BK-SUR-ENG-MEC-01-07139 | 2023-03-07 | Noted
3 | در خط دوم بند7، عبارت "Supplier" به عبارت "Vendor" تغيير يابد. |  | BK-SUR-ENG-MEC-01-07139 | 2023-03-07 | Noted
4 | در جدول Attachment 2: -در رديف 1، عبارت "See Attachment 2" حذف گردد. - عبارت "List of Documents will be Finalized in VPIS" در نوتها اضافه گردد. - مدارك SAT Procedure اضافه گردد. - در رديف 084، عبارت "5.1.3" حذف گردد. |  | BK-SUR-ENG-MEC-01-07139 | 2023-03-07 | Noted
5 | لزوم ارائه مدارك ITP, QCP, MPS توسط سازنده قبل از برگزاري جلسه PIM در مدرك درج گردد. |  | BK-SUR-ENG-MEC-01-07139 | 2023-03-07 | Noted
6 | در بند 5.1.2 شماره مدرك به صورت صحيح E&C-QC-SP-1 آورده شود. |  | BK-SUR-ENG-MEC-02-07573 | 2023-09-05 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته است
7 | جهت يكسان سازي در كليه مدارك MR پروژه، نگارش توضيحات بند6 مطابق ذيل انجام گردد. |  | BK-SUR-ENG-MEC-02-07573 | 2023-09-05 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته است
The equipment shall be inspected and tested in accordance with the Inspection &Test plan (ITP) issued by the vendor and approved by the CLIENT/EPC CONTRACTOR before the award of the order . The Inspection & Test plan (ITP ) shall be at least according to the Commodity Procurement and Manufacturing Inspection Instruction ( Docs .Nos. ICE-EID-MI-SP01-Rev01) , Inspection Level of Commodity and Equipment ( Docs .Nos. ICE-EID-MI-SP02-Rev01) and Data Sheets. The vendor shall in any case conduct all the tests required by contractual documents, specifications, codes and standards, manufacturer standard quality system and keep the relevant documentation. All required manufacturing and function test/inspection also Factory Acceptance Test /Site Acceptance Test and Quality Assurance requirements shall be considered in vendor responsibility as per project specification.
8 | در بند (PRICE BREAKDOWN) ، در آيتمهاي شماره 3,2، شماره مدرك بصورت صحيح E&C-QC-SP-1 وارد گردد |  | BK-SUR-ENG-MEC-02-07573 | 2023-09-05 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته است
9 | در جدول Attachment 1 درقسمت General ، شماره مدرك "دستورالعمل تامين قطعات يدكي راه اندازي و راهبري دوسالانه" به صورت صحيح E&C-QC-SP-1 آورده شود. |  | BK-SUR-ENG-MEC-02-07573 | 2023-09-05 | نقطه نظر کارفرمای محترم مد نظر قرار گرفته است
INSTRUMENT COMMENTS:
1 | فايل پيوست مشاهده گردد. |  | BK-SUR-ENG-MEC-02-08303 | 2023-08-20 | Noted
2 | عبارات “A PLC based UCP mounted in control room for air compressor as authorized master logic controller of complete air package. Standalone microprocessor based control panel located on dryer skid for all required signaling, local logic, monitoring and etc. which shall be connected to control room mounted UCP of air compressor. UCP shall be connected to the PCS, ESD, for required monitoring, control functions and shutdowns as per P&ID. UCP panel door shall including alarm, trip and interlock logic; annunciator lamp and buzzer; push button switches; Terminal box, if UCP is control room mounted , required LCP for local command isrequired.” در خصوص پكيج هوا و عبارت "A PLC based UCP mounted in control room for each Nitrogen package. UCP shall be connected to the PCS, ESD, for required monitoring, control functions and shutdowns as per P&ID. UCP panel door shall including alarm, trip and interlock logic; annunciator lamp and buzzer; push button switches; Terminal box, if UCP is control room mounted , required LCP for local command is required." در خصوص پكيج N2 با مدرك Block Diagram for GCS Control تناقض دارد و مورد تاييد اين امور و كارفرما نيز نمي باشد. براي پيشبرد گام بعدي مهندسي پيشنهاد مي گردد كه اين موارد از مدرك حذف و به مدارك مربوط به spec و Block Diagram ارجاع داده شود. |  | BK-SUR-ENG-MEC-01-07140 | 2023-03-08 | مورد ذکر شده مطابق آخرین توافقات در Spec های ضمیمه شده به این مدرک و سایر مدارک مهندسی از جمله P&ID و یاگرامهای کنترلی …پیاده شده است. به دلیل تاکید بیشتر و جلوگیری از خطا متن صریح آن در PMR نیز آورده شده است.
3 | توضيح ارائه شده براي پكيج Dryer با مدرك P&ID در خصوص نوع پكيج تناقض دارد. همسان سازي بين مدارك در نظر گرفته شود. |  | BK-SUR-ENG-MEC-02-07573 | 2023-05-10 | تیپ کنترلی پکیج درایر A می باشد که از طریق پکیج تایپ Cکمپرسور با سیستم DCS در ارتباط است.مطابق P&ID سیگنال های RUNNING STATUS , COMMON FULT ALARM با شماره های XR-2201 , XF-2201 از طریق UCP کمپرسور به DCS ارسال می شود توضیحات MR نیاز به اطلاح ندارد . نوت 9 توضیحات اضافه در مورد بخش درایر در P&ID آورده شده است
Legend | Comment Sheet Status: (By Client) C1: Reviewed with no comment (No Response required) C2: Reviewed with minor comment ( work may proceed and comments to be addressed and incorpated prior to issue) C3: Reviewed with major comment (Revise and resubmit. Work may not be proceeded until the document is returned with code C1 &C2) C4: Rejected ( Deviated from the project requirement. Resubmit for Review) C5: Issued for information (No Response required)
Signature | CLIENT (NISOC/PEDCO) |  |  |  |  | EPC Contractor
| Commented By: M. Torkaman Ah.behbahani | Signature | H.Naserizadeh |  |  | Clarified By: S.Zafaresmaeili | Signature | M.Fakharian
| Date : 10/5/2023 |  |  |  |  | Date: 28/AUG/2023